## Product Backlog
Product Name: | Exceptional Laptops and Supercomputers Always (ELSA) | [6 empty] | Complete Fields in Green!!!
Team ID: | Suggested Solution
| Team Member Name | [5 empty] | Initials | Student ID
Required | Professor Rice | [5 empty] | GFR | 1
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 23 |  |  |  | Total | Total number of features (in column H)
1 | 19 | 4 |  |  | 1 | Total features left at the end of Sprint #1
2 | 15 | 4 |  |  | 2 | Total features left at the end of Sprint #2
3 | 12 | 3 |  |  | 3 | ...and so on
4 | 6 | 6
5 | 0 | 6
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CUST | 1 | 1 |  | 3 | 1 | Finished in Sprint 1 | Sales Staff | Remember each customer’s name and contact info | Ship them products repeatedly
OPT | 2 | 1 |  | 8 | 1 | Finished in Sprint 1 | Inventory | Maintain a list of options for a desktop (e.g., disk, RAM, CPU) | Select them when designing a new desktop product
DESKT | 3 | 1 |  | 8 | 1 | Finished in Sprint 1 | Sales Staff | Define a new desktop configuration from options | Can quickly customize products for my customers
ORDER | 4 | 1 |  | 13 | 1 | Finished in Sprint 1 | Sales Staff | Associate a customer with one or more desktops into an order | Keep track of who has bought what
WIN | 5 | 2 |  | 21 | 2 | Finished in Sprint 2 | Sales Staff | Replace text interface with GUI main window | Use it more easily | Recommend baselining Nim from Lecture 13
OUTM | 6 | 2 |  | 5 | 2 | Finished in Sprint 2 | Sales Staff | Replace list of data records with main window list | Access the data directly in the window | Try using std::ostringstream to capture operator<< formatting
INDIA | 7 | 2 |  | 8 | 2 | Finished in Sprint 2 | Sales Staff | Replace data queries with series of dialogs | Do everything within the GUI | Recommend baselining EntryDialog from Lecture 14
ABOUT | 8 | 2 |  | 1 | 2 | Finished in Sprint 2 | Director | Provide About dialog for documenting licenses | Avoid a lawsuit
SAVE | 9 | 3 |  | 13 | 1 | Finished in Sprint 3 | Manager | Save the data to a default file (File > Save) | Persist our data through the years | This requires modifying the “model” to save and reload each object from a provided stream
SAVAS | 10 | 3 |  | 5 | 2 | Finished in Sprint 3 | Manager | Save the data to a specified file (File > Save As) | Persist our data through the years | Use Gtk::FileChooser
LOAD | 11 | 3 |  | 8 | 3 | Finished in Sprint 3 | Manager | Load the data from a specified file (File > Open) | Persist our data through the years | Use Gtk::FileChooser
QRAM | 12 | 4 |  | 21 | 1 | Finished in Sprint 4 | Customer | Store and display additional RAM data | Ensure I purchase the correct product
DCUST | 13 | 4 |  | 8 | 2 | Finished in Sprint 4 | Sales Staff | Replace Insert Customer dialogs with single dialog | Enter data more quickly
Mainwin | 14 | 4 |  | 13 | 3 | Finished in Sprint 4 | Sales Staff | Relplace mainwin , add another method. | Enter data more quickly
BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!
QCPU | 14 |  | 25 | 13 | 1 | Finished in Sprint 4 | Customer | Store and display additional CPU data | Ensure I purchase the correct product | Derive classes from Options and call operator<< polymorphically
QDISK | 15 |  | 10 | 5 |  | Finished in Sprint 4 | Customer | Store and display additional Disk data | Ensure I purchase the correct product
DORD | 16 |  | 15 | 8 |  |  | Sales Staff | Replace Insert Order dialogs with single dialog | Enter data more quickly
DOPT | 17 |  | 40 | 21 | 2 | Finished in Sprint 4 | Sales Staff | Replace Insert Option dialogs with single dialog | Enter data more quickly
DDESK | 18 |  | 25 | 13 |  |  | Sales Staff | Replace Insert Desktop dialogs with single dialog | Enter data more quickly
TBAR | 19 |  | 10 | 5 |  |  | Customer | Access key functionality with a toolbar AND menu | More quickly access the behaviors I need | You can baseline this code from Nim’s Mainwin::Mainwin as well
SCROL | 20 |  | 10 | 5 |  |  | Customer | Make the main window’s data area scrollable | See large volumes of data | The exact settings (e.g., are the scrollbars always visible or only when scrolling is available?) are up to you
DEPR | 21 |  | 25 | 13 |  |  | Inventory | Deprecate a product | Avoid selling products that are out of production | This requires a Boolean with getter and setter in the Options and Desktop classes to indicate which are deprecated. The index number may pose interesting challenges, since deprecation will create gaps.
SBAR | 22 |  | 15 | 8 |  |  | Manager | Replace the Gtk::Label for the status bar with Gtk::Statusbar, and maintain a message stack | Better track status of messages | Just swapping Gtk::Statusbar for Gtk::Label is trivial. Think through how to manage a first-in last-out stack of messages

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2020-03-03 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-03-24
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 16
Day 1 Left | 10 | 6
Day 2 Left | 10 | 0
Day 3 Left | 7 | 3
Day 4 Left | 3 | 4
Day 5 Left | 3 | 0
Day 6 Left | 2 | 1
Day 7 Left | 0 | 2
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CUST |  | Write the Customer class | Completed Day 1 | Test each class and method as it is written
2 | CUST |  | Write operator<< for Customer | Completed Day 1 | Commit and push AT LEAST once every class or update
3 | CUST |  | Write Store::add_customer, num_customers, and customer | Completed Day 1 | You are free to determine your own algorithm for mapping the (now) 21 days of this sprint to the 7 reporting days – e.g., 1/3 days, the first 7 days you actually do work, etc.
4 | OPT |  | Write the Options class sans to_string | Completed Day 1
5 | OPT |  | Write Options::to_string and its operator<< | Completed Day 1
6 | OPT |  | Write Store::add_option (to Store), num_options, and option | Completed Day 1
7 | DESKT |  | Write the Desktop class with add_option method | Completed Day 3
8 | DESKT |  | Write the Desktop::price method | Completed Day 3
9 | DESKT |  | Write operator<< for Desktop | Completed Day 3
10 | DESKT |  | Write Store::new_desktop, add_option (to desktop), num_desktops, and desktop | Completed Day 4
11 | ORDER |  | Write the Order associative class and constructor | Completed Day 4
12 | ORDER |  | Write Order::add_product | Completed Day 4
13 | ORDER |  | Write Order::price | Completed Day 4
14 | ORDER |  | Write Store::new_order, add_desktop, num_orders, and order | Completed Day 6
15 | ORDER |  | Integrate and test with cse1325_prof/elsa/sprint_1/main.cpp | Completed Day 7
16 | ORDER |  | Ensure ALL CODE is on GitHub by deadline! | Completed Day 7
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2020-03-24 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-03-31
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 15
Day 1 Left | 15 | 0
Day 2 Left | 4 | 11
Day 3 Left | 4 | 0
Day 4 Left | 1 | 3
Day 5 Left | 0 | 1
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | WIN |  | Baseline mainwin.h and .cpp, and main.cpp, from Nim (Lecture 13) | Completed Day 2
2 | OUTM |  | Write set_data and set_msg methods | Completed Day 2 | These centralize updating the data areas of the main window
3 | WIN |  | Baseline entrydialog.h and .cpp from Lecture 14 | Completed Day 2 | This replaces std::getline with a simple dialog equivalent
4 | INDIA |  | Write get_string method | Completed Day 2 | This encapsulates EntryDialog with code to just return string
5 | INDIA |  | Write get_double and get_int methods | Completed Day 2 | These use get_string and error handling to return numbers
6 | WIN |  | Update mainwin.h to reflect ELSA design | Completed Day 2 | Add pointers to store, data area, and status message. Declare observers (callbacks). Comment out toolbard, unless you’d prefer to keep it (it’s a bonus feature!)
7 | WIN |  | Update main.cpp to reflect ELSA design | Completed Day 2 | Basically change 3rd parameter of Gtk::Application::create
8 | WIN |  | Iterate through mainwin.cpp, fixing errors until elsa compiles | Completed Day 2 | Define empty callbacks. Delete obsolete callbacks. Etc.
9 | WIN |  | Modify the main menu code in Mainwin::Mainwin to reflect ELSA | Completed Day 2 | Make the UI look and operate correctly, even though nothing happens when you select a menuitem (yet)
10 | INDIA |  | Copy “create customer” code from previous sprint’s main.cpp, and adapt to GUI’s Insert > Customer callback | Completed Day 2 | Use get_string utility method to replace getline calls
11 | OUTM |  | Copy “show customers” code from previous sprint’s main.cpp, and adapt to GUI’s View > Customer callback | Completed Day 2 | Use output string string in place of std::cout, with fixed and setprecision(2), and put result into main data area with Pango. Fix options.cpp formatting bug.
12 | INDIA |  | Migrate code from main.cpp to mainwin.cpp for Options | Completed Day 4
13 | INDIA |  | Migrate code from main.cpp to mainwin.cpp for Desktop | Completed Day 4
14 | INDIA |  | Migrate code from main.cpp to mainwin.cpp for Orders | Completed Day 4
15 | ABOUT |  | Update Help > About code for ELSA | Completed Day 5
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2020-03-31 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-07
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 8
Day 1 Left | 7 | 1
Day 2 Left | 4 | 3
Day 3 Left | 4 | 0
Day 4 Left | 4 | 0
Day 5 Left | 3 | 1
Day 6 Left | 2 | 1
Day 7 Left | 0 | 2
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CUST |  | Added istream and ostream to load data | Completed Day 1
2 | OPT |  | Added streams for file handling | Completed Day 2
3 | DESKT |  | Added streams for file handling | Completed Day 2
4 | ORDER |  | Used customer pointer and heap memory for file | Completed Day 2
5 | WIN |  | Added 4 new features to the menu | Completed Day 5
6 | SAVE |  | Added save to save data from the user by defualt | Completed Day 6
7 | SAVAS |  | Added save as to save data in different formats and files | Completed Day 7
8 | LOAD |  | Loaded data to be able to view when opening the file | Completed Day 7
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2020-04-14 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-28
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 7
Day 1 Left | 7 | 0
Day 2 Left | 7 | 0
Day 3 Left | 7 | 0
Day 4 Left | 7 | 0
Day 5 Left | 7 | 0
Day 6 Left | 3 | 4
Day 7 Left | 0 | 3
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | OPT |  | Use const to override. | Completed Day 6 | You are free to determine your own algorithm for mapping the (now) 21 days of this sprint to the 7 reporting days – e.g., 1/3 days, the first 7 days you actually do work, etc.
2 | QRAM |  | .cpp implementation of RAM | Completed Day 6
3 | QRAM |  | .h implementation of RAM | Completed Day 6
4 | WIN |  | Custom dialog for easy implementation of data | Completed Day 6
5 | QCPU |  | Added CPU.cpp and .h with their implementation | Completed Day 7
6 | DOPT |  | Added a single dialog box for options! | Completed Day 7
7 | QDISK |  | Added CPU.cpp and .h with their implementation | Completed Day 7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84